## Sheet1
Element | Project Description | Lead staff | Resources Needed | Implementation Strategy | Time frame | Partners | Priority
CA Watershed Assessments Version 1 | Display interactive maps of CA HWI assessments on MyWaterQuality portals | Lori/SWAMP unit, GIS staff | Staff time | Existing staff | Michelle checking with SB GIS unit on level of effort and time |  | High
| Combine Health and Vulnerability scores into one map for California and display on Healthy Watersheds Portal (aka "Wisconsin map") | Terry, Pete, Lori/SWAMP | Staff time Contract/grant funding? | Existing staff (?)
CA Watershed Assessments, Version 2 and beyond | Test existing HWI predictions and recommend improvements | Pete, Andy | ??
| Super toggle to allow user-selected comparisions of CA HWI assessments | Lori/SWAMP, GIS staff, Pete, Andy | Staff time Contract/grant funding?
| Develop sub- metrics responsive to stressors | SWAMP, CDFW, others? | Staff and funding
| Integrate benefical use, TMDL and Integrated Report data into CA HWI assessments | TBD | Staff time Contract/grant funding?
| Integrate CA HWI assessment data layers into Integrated Report | Terry Fleming w/Nick Martorano, Jeff Kapellas | Staff time Contract/grant funding?
| Integrate CA HWI assessments into State Water Plan updates through Sustainability Indicators project | Fraser Shilling (?) | Staff and funding
| Investigate report card approach to integrate multiple datasets | Karen W., Chris Solek, Brock B., (Chad L.) | Staff and funding | Grant proposal | ~3 years
My Water Quality Portal Enhancements | Add algae, pHAB and CRAM data to HW Portal | SWAMP & GIS unit staff | Staff time | Existing staff | Dependent on staff time, may be linked to OIMA storytelling
| Add pesticides from SPoT and DPR use to stressors pages | SWAMP & GIS unit staff | Staff time Contract/grant funding? | Existing staff | Dependent on staff time, may be linked to OIMA storytelling
| Map CSCI (both E andO/E) and other metrics on HW Portal | SWAMP, GIS unit staff, Pete, Andy | Staff time Contract/grant funding? | Existing staff | Dependent on staff time, may be linked to OIMA storytelling
| Minimum flow requirements (fish) and flow ecology (bugs/algae) information on HW Portal | SWAMP, GIS unit staff, Pete, Andy | Staff time Contract/grant funding? | Existing staff | Dependent on staff time, may be linked to OIMA storytelling
| Incorporate CEDEN data into HW Portal | Lori and SWAMP unit staff | Staff time Contract/grant funding? | Existing staff | Long term/dependent on revised CEDEN
| Implement Region 3 data navigator tools statewide | Karen W., John Hunt | Staff time and funding | Grant proposal
| Disseminate SWAMP SOPs, QA/QC, data management, and other tools to additional monitoring programs throughout the Water Boards and other agencies and organizations | SWAMP unit staff | Staff time | Links on Portal
| Incorporate TMDL report cards, NPS success stories, and other watershed based reporting into the Portal | SWAMP, NPS, TMDL staff and others | Staff time | Existing staff | Dependent on staff time, may be linked to OIMA storytelling
Outreach & Partnerships | Improve partnerships with CDFW's SWAP, Areas of Conservation emphasis; and TNC freshwater biodiversity database, USFS Ecological Healthy, CalFire | All | Staff time, but may lead to identification of additional projects requiring resources | Outreach, agenda items, links on Portal, eventually grant proposals | Ongoing | CDFW, TNC, USFS, CalFire
| Improve assistance to citizen monitoring groups, communicate non-healthy/vulnerable watersheds | Erick Burres, all | Staff time, but may lead to identification of additional projects requiring resources | Outreach, agenda items, links on Portal, eventually grant proposals | Ongoing | Many
| Improve partnerships with agencies and non-profits concerned with watershed management | All | Staff time, but may lead to identification of additional projects requiring resources | Outreach, agenda items, links on Portal, eventually grant proposals | Ongoing | DOC, RCDs, watershed groups, regional offices